## Gantt
FHIR AI ENABLED APPEAL FOR RFA PAIN MANAGEMENT THERAPY | [5 empty] | Legend:
Weekdays at 830 | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
|  | Project Start Date: |  | 2019-02-15
|  | Display Week: |  | 1 |  | February | [20 empty] | March | [27 empty] | April
 | time axis 2019-02-11 to 2019-04-24
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
Milestone Description | Category | Assigned To | Progress | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
Title 1
Deliverable 1 | On Track | Cameron | 100% | 2019-02-15 | 3
Research RFA Appeal Process | On Track | All | 100% | 2019-02-15 | 5
Research Technologies | On Track | All | 100% | 2019-02-15 | 5
Research ML/NLP .Net Libraries | On Track | Zhe | 100% | 2019-02-20 | 7
Research PubMed Api | On Track | Zhoumeng, Ting | 100% | 2019-02-20 | 7
Create Docker Container for Client | On Track | Kai | 100% | 2019-02-20 | 7
Create Docker Container for Server | On Track | Richard, Cameron | 100% | 2019-02-20 | 7
Stand up server with basic web API functionality | On Track | Richard, Cameron | 100% | 2019-02-27 | 10
Research What Info is Relevant to the Appeal | On Track | Zhoumeng | 100% | 2019-02-27 | 7
Create Test Application to Retrieve Relevant Data from HDAP | On Track | Richard, Cameron | 100% | 2019-03-01 | 10
Add basic UI to client | High Risk | Ting, Kai | 100% | 2019-03-01 | 28
Deliverable 2 | Low Risk | Cameron, Zhe | 100% | 2019-03-07 | 7
Modify App to Add Insights into the Appeal Process using PubMed API | Med Risk | Zhoumeng, Ting, Cameron, Richard | 100% | 2019-03-11 | 14
Modify App to Generate Appeal | Low Risk | Zhoumeng, Ting, Cameron | 100% | 2019-03-15 | 5
Investigate/Implement NLP | High Risk | Zhe | 100% | 2019-03-20 | 21
Get build servers working using Jenkins and Rancher | Low Risk | Cameron | 100% | 2019-03-20 | 14
Deliverable 3 | Low Risk | Kai, Ting | 100% | 2019-03-25 | 7
Add regex matching to solution | Low Risk | Cameron | 100% | 2019-03-30 | 7
Add remaining UI functionality | High Risk | Kai, Cameron | 100% | 2019-03-30 | 17
Deliverable 4 | Low Risk | Zhoumeng, Richard | 100% | 2019-04-15 | 7

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. Change the display week number to change the timeline view. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with input messages. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. To remove these instructions from the worksheet, go to Data > Data Tools > Data Validation > Input Message and delete them.
This is the last instruction in this worksheet.